E Don Kast — Implementation Brief

One-Page Deployment & Adoption Roadmap  |  ADC 2026

# Implementing Actors & Roles

| Actor | Role | Deliverable |
| --- | --- | --- |
| StayGIS LLC | Platform owner | E Don Kast infrastructure, Claude Vision pipeline, API integrations |
| CCIJ | Data partner | 169,328 digitized EC8A forms; ongoing digitization pipeline |
| SERAP / NBA | Legal co-signatories | Validate outputs as evidence; file tribunal complaints |
| INEC | Compliance enforcer | Mandate structured data exports under Electoral Act 2026 regulations |
| Diaspora Networks | Funders / validators | $50k seed funding; ground-truth verification in home wards |

# Estimated Budget (Phase 1 Pilot — 90 Days)

| Line Item | Estimate (USD) | Notes |
| --- | --- | --- |
| Claude Vision API (Haiku, 50k forms) | $4,000 | ~$0.08/form |
| Platform infrastructure (cloud hosting, DB) | $6,000 | 3-month pilot |
| Legal partnership setup (SERAP/NBA MOU) | $5,000 | One-time |
| Community outreach & ward captain training | $10,000 | Obio-Akpor LGA |
| Human review QA (10% confidence-flagged forms) | $8,000 | Crowd-verified |
| Reserve / contingency (15%) | $4,950 |  |
| TOTAL | $37,950 | Phase 1 only |

# 90-Day Rollout Roadmap

| Phase | Milestones | Success Metrics |
| --- | --- | --- |
| Days 1–30 | CCIJ data pipeline connected; 10,000 forms processed; dashboard live; SERAP MOU signed | ≥95% extraction accuracy; dashboard publicly accessible |
| Days 31–60 | Obio-Akpor LGA fully processed; ward-captain QA network deployed; first discrepancy report published | ≥3 LGA-level discrepancy reports filed with SERAP |
| Days 61–90 | Expand to all 5 flagged Rivers State LGAs; INEC structured data request submitted; open-source release | 5 LGAs covered; INEC formal response received; 1 tribunal evidence packet submitted |

# Risk Register

| Risk | Severity | Likelihood | Mitigation |
| --- | --- | --- | --- |
| INEC blocks API access or structured data | High | Medium | Maintain IReV image pipeline as fallback; public pressure via civil society |
| Legal challenge to admissibility of AI-extracted evidence | High | Medium | Human review confirmation for all tribunal-bound outputs; SERAP co-signature |
| Electoral Act 2026 "communication failure" exemption exploited | Medium | High | Log exemption claims; publish per-ward failure rates to create accountability pressure |
| Form image quality too low for AI extraction | Medium | Low | Confidence threshold routing; crowd-verification fallback for low-quality images |
| Funding gap after Phase 1 | Low | Low | Diaspora campaign (NIDO, NANAF); CCIJ/Veza co-funding for Phase 2 |
| Political pressure to suppress platform | High | Low | Open-source release; distributed data storage; international civil society co-ownership |

Prepared by Team 16 for ADC 2026, Track 3  |  Contact: femi@staygis.com